|  | 7 MTPA INTEGRATED PELLETIZATION PROJECT NASHWAUK, MINNESOTA | M M C L 17113 COUNTY RD. 58 MN 55769 |
| --- | --- | --- |
|  | NOTE FOR APPROVAL |  |

| Project: | 7 MMTPA iron ore pellet plant (Mesabi Metallics Company LLC) |  |  |
| --- | --- | --- | --- |
| Item Description: | Supply of Softwater Plant for Pellet plant cooling system – 1 Unit. |  |  |
| NTD Ref No: | MMCL/2024-25/PROC/NFA/312 | NFA Date: | 10th March 2025 |
| Indent No: | MMCL/PME/GEN/MER/PR-320 Rev-01 | Technical Specification ref |  |
| SAP PR No: |  | Technical Specification Date |  |
| WBS: | M-1017-G-PME-GEN-MER | WBS Budget total | USD 10,796,095.43 |
|  |  | WBS Budget balance | USD 5,587,931.63 |
|  |  | Value of current NFA | USD 85,500.00 |
|  |  | Estimate value for balance WBS | USD 5,502,431.63 |

- DESCRIPTION OF THE PACKAGE:

This note covers Supply of Softwater Plant for Pellet plant cooling system – 1 Unit required for 7 MMTPA Beneficiation and Pelletization plant for Mesabi project at Nashwauk, MN, USA.

Action taken-

Upon restart of the project, it was strategized to explore sourcing this Softwater Plant for Pellet plant cooling system – 1 Unit. and hence suitable vendors manufacturing these items were identified, who can supply as per MMCL, MN, USA specification requirement.

Accordingly, enquiry was floated to the following vendors: -

- WTE INFRA PROJECTS PVT LTD. (India) - offer submitted.

- ION EXCHANGE (India) - offer submitted.

- Doshi Ion (India) - offer submitted.

- Kurita (USA)- Partial offer submitted.

- Landmark (India) - Partial offer submitted.

Technical offers were evaluated by our Engineering team, and all vendors were technically acceptable.

Price Comparison of Technically acceptable vendors

| Supplier | WTE INFRA PROJECTS PVT LTD, PUNE (India) | DOSHION (India) | ION EXCHANGE (India) |
| --- | --- | --- | --- |
| Offer Ref | Mail Dt: 2 March 026 | DEWS/AE/25-26/76/R1 Date: 7th March 2026 | IEI/3271/12/USA/6138/SMA/R5 Date: 17.02.2026 |
| Supply of Softwater Plant for Pellet plant cooling system – 1 Unit. | 95,000.00 | 107,247.31 | 236,000.00 |
| Negotiated Price ($) | 85,500.00 | 107,247.31 | 214,500.00 |
| Freight Cost ($) (Estimated)** | 12,000.00 | 12,000.00 | 12,000.00 |
| Import Duty & Tariff Value ($) (Estimated)** | 15,390.00 | 19,304.52 | 38,610.00 |
| Total (Landed Cost) ($) | 112,390.00 | 138,551.83 | 265,110.00 |
| Delivery | 10 weeks from Date of PO. | 16-18 weeks from the date of receipt of manufacturing clearance | Delivery will be 7 months on FOB Mumbai/JNPT basis from the date of commercially clear PO with advance. |
| Technical Evaluation | Technically Acceptable | Technically Acceptable | Technically Acceptable |
|  | L1 | L2 | L3 |

- RECOMMENDATION:

It is recommended to place purchase order on WTE INFRA PROJECTS PVT LTD., PUNE (India). L-1, with brief terms & conditions negotiated are as listed below:

| Final Value | USD 85,500.00 FOB JNPT, Mumbai MH, India, Basis. as per final technical scope agreed during technical evaluation. Insurance cost to the account of MMCL. |
| --- | --- |
| Payment Terms | - 20% advance along with Order against submission of Bank Guarantee. - 20% against drawing approval. - 55% payment will be made upon material readiness, after successful inspection and prior to dispatch. - 5% Performance Bank Guarantee (PBG) valid for the entire warranty period (18 months from installation or 24 months from dispatch, whichever is earlier). |
| Delivery Schedule | 10 weeks from the date of Purchase Order. GA Drawing Submission Within 1 week from the date of PO release |
| Warranty Period | 18 months from the date of acceptance after inspection of the equipment or 24 months from the date of commissioning whichever is earlier. |
| Other Terms & Conditions | As per STC & GTC. |
| ABG & PBG | ABG: 20% and PBG: 5% of the total PO value. |

In view of above, it is recommended to place order for the Softwater Plant for Pellet plant cooling system – 1 Unit. with M/s. WTE INFRA PROJECTS PVT LTD., PUNE (India).  for Value USD 85,500.00 FOB JNPT, Mumbai MH, India, Basis.

| Prepared & Initiated By | NITIN SHETTY / SATYEN SINHA |  |
| --- | --- | --- |
| Cost Control | MAHESH KOMMURU / MANINDRA AGRAWAL |  |
| Finance & Accounts | SUNIL AGRAWAL / LALIT RUSTAGI |  |
| Recommendation & Approval Committee | SUBBARAO NAMALA |  |
|  | MOHAMMAD RIZWAN |  |
| Approved By | RAKESH KANKANALA |  |
|  | AMIT SWARNKAR |  |

Enclosed:

- Latest offer from vendor.