|  | 7 MTPA INTEGRATED PELLETIZATION PROJECT NASHWAUK, MINNESOTA | M M C L 17113 COUNTY RD. 58 MN 55769 |
| --- | --- | --- |
|  | NOTE FOR APPROVAL |  |

| Project: | 7 MMTPA iron ore pellet plant (Mesabi Metallics Company LLC) |  |  |
| --- | --- | --- | --- |
| Item Description: | Supply of Fabricated Tech Structures including Rubber Lining and Painting |  |  |
| NTD Ref No: | MMCL/2025-26/PROC/NFA/260 | NFA Date: | 19th Dec 2025 |
| Indent No: | MMCL/PST/HLB-IND-CB1/TCH/PR-304 | Technical Specification ref |  |
| SAP PR No: |  | Technical Specification Date |  |
| WBS: | M-1017-P-PST-HLB-TCH | WBS Budget total | USD 111,300.57 |
|  |  | WBS Budget balance | USD 111,300.57 |
|  |  | Value of current NFA | USD 12,975.50 |
|  |  | Estimate value for balance WBS | USD 98,325.07 |
| WBS: | M-1017-P-PME-IND-MER | WBS Budget total | USD 3,540,665.54 |
|  |  | WBS Budget balance | USD 1,506,398.98 |
|  |  | Value of current NFA | USD 34,677.60 |
|  |  | Estimate value for balance WBS | USD 1,471,721.38 |
| WBS: | M-1017-C-PST-CB1-SSE | WBS Budget total | USD 5,958,277.96 |
|  |  | WBS Budget balance | USD 4,420,810.78 |
|  |  | Value of current NFA | USD 50,481.90 |
|  |  | Estimate value for balance WBS | USD 4,370,328.88 |

- DESCRIPTION OF THE PACKAGE:

This note covers the Supply of Fabricated Tech Structure (56.33 MT) required for 7MTPA Beneficiation and Pelletization plant for Mesabi project at Nashwauk, MN, USA.

| SR. NO. | Items | Weight in MT |
| --- | --- | --- |
| 1 | Hearth Layer Product chutes (4170.CH.103 & 4170.CH.105) | 4.50 |
| 2 | Hearth Layer Separation chutes (4170.CH.103 & 4170.CH.106) | 3.72 |
| 3 | Filtrate Collection Tank (4065.TK.121/122) | 12.92 |
| 4 | Concorde Feed Sump (2120.FS.101,301) | 23.46 |
| 5 | Concorde Feed Sump ( 2120.FS.201) | 11.72 |
|  | TOTAL | 56.33 |

- Action taken-

It was strategized to explore for the Supply of Fabricated Tech Structure (56.33 MT) and hence suitable vendors fabricating these items were identified, who can supply as per MMCL, MN, USA specification requirements.

Accordingly, enquiry was floated to the following vendors:

- M/s Karbonsteel Engineering Limited, India – Offer submitted

- M/s Fabmax Enterprise, India – Offer submitted

- M/s True North Steel, USA – Partial offer submitted

- M/s Be’RolleX Pvt. Ltd., India – Offer submitted

- M/s Agra Industries, USA – Offer not submitted

2. Technical Evaluation:

The Technical team reviewed and evaluated the submitted offers and confirmed that M/s Fabmax Enterprise, India, M/s Karbonsteel Engineering Limited, India, and M/s Be’RolleX Pvt. Ltd., India meet the MMCL technical requirements and are therefore technically acceptable. M/s True North Steel, USA has offered only for fabrication and painting which meets MMCL requirement.

3. Price Comparison for Technically Acceptable Vendor

| Supplier | Fabmax Enterprise (India) | Be’RolleX Pvt. Ltd (India) | Karbonsteel Engineering Limited (India) | True North Steel (USA) |
| --- | --- | --- | --- | --- |
| Quotation Reference No. | FM-202526Q204 | QTN/10:2025/4181/REV-05 | KSPL/EML/Q-157/R4/25-26 | Email Reference |
| Quotation Date & Email Ref. Date | 18-Dec-2025 | 03-Dec-2025 | 12-Dec-2025 | 11-Dec-2025 |
| Quoted Prices ($) | 212,545.00 | 231,758.40 | 105,017.00 | 538,923.00 |
| Negotiated Price ($) | 200,255.00 | 118,416.30 | 98,135.00 | 538,923.00** |
| Import Tariff ($) @50% | 100,127.50 | 59,208.15 | 49,067.50 | NA |
| Freight Cost (1 x 40' HC & 3 FR containers) ($) (Estimated)* | 88,000.00 | 88,000.00 | 88,000.00 | 4,950.00 |
| Total (Land Cost) ($) | 388,382.50 | 265,624.45 | 212,582.50 | 543,873.00 |
| Lead time | 16-18 weeks from PO (8-10 weeks for fabrication and 8 weeks for shipment) | 16-18 weeks from PO (8-10 weeks for fabrication and 8 weeks for shipment) | 12-15 weeks from PO (4 - 7 weeks for fabrication and 8 weeks for shipment) | 18-20 weeks from PO |
| Technical Evaluation | Technically Acceptable | Technically Acceptable | Technically Acceptable | Technically Acceptable** |
|  | L3 | L2 | L1 | L5 |

* According to Section 232: A 50% tariff is applicable on the import of steel and aluminium products into the USA from all countries.

** M/s True North Steel, USA has offered only for fabrication and painting. For price comparison, previously executed M/s IRACORE, USA price has been considered for rubber lining.

Final No-Regret Offer is taken from M/s Karbonsteel Engineering Limited, India and is attached as per Enclosure – 1.

B. RECOMMENDATION:

It is recommended to place purchase order on M/s Karbonsteel Engineering Limited, India, with brief terms & conditions negotiated are as listed below:

| Final Value | USD 98,135.00 (Ex-Works Basis) as per final technical scope agreed during technical evaluation. Freight & Insurance cost to the account of MMCL. |
| --- | --- |
| Payment Terms | 100% payment against material readiness duly inspected before dispatch on pro-rata basis. |
| Delivery Schedule | Progressive delivery from 4 to 7 weeks from the date of PO |
| Warranty Period | 18 months from commissioning or 24 months from last supply, whichever is earlier. |
| Other Terms & Conditions | As per STC & GTC. |
| ABG & PBG | NA |

C. REASONS FOR RECOMMENDATION:

- M/s Karbonsteel Engineering Limited, India is commercially L1, and they are technically acceptable.

- M/s Karbonsteel Engineering Limited, India has a good performance track record as per enclosure-4.

In view of above, it is recommended to place order for Supply of Fabricated Tech Structure (56.33 MT) with M/s Karbonsteel Engineering Limited, India for Value USD 98,135.00 (Ex-Works Basis).

| Prepared & Initiated By | VIHANG MEHTA / SATYEN SINHA |  |
| --- | --- | --- |
| Cost Control / Planning | MAHESH KOMMURU / MANINDRA AGRAWAL |  |
| Finance & Account | SUNIL AGRAWAL / LALIT RUSTAGI |  |
| Recommendation & Approval Committee | SUBBARAO NAMALA |  |
|  | MOHAMMAD RIZWAN |  |
| Approved by | RAKESH KANKANALA |  |
|  | AMIT SWARNKAR |  |

Enclosure:

- Final No-regret Offer and email reference from M/s Karbonsteel Engineering Limited, India

- Technical Clearance email for M/s Karbonsteel Engineering Limited, India from Techncial Team

- PR-304 copy

- PTR from M/s Karbonsteel Engineering Limited, India