|  | 7 MTPA INTEGRATED PELLETIZATION PROJECT NASHWAUK, MINNESOTA | M M C L 17113 COUNTY RD. 58 MN 55769 |
| --- | --- | --- |
|  | NOTE FOR APPROVAL |  |

| Project: | 7 MMTPA iron ore pellet plant (Mesabi Metallics Company LLC) |  |  |
| --- | --- | --- | --- |
| Item Description: | Modification of Slurry Pumps for Line 1 & 2 |  |  |
| NTD Ref No: | MMCL/2025-26/PROC/NFA/317 | NFA Date: | 18th March 2026 |
| Indent No: | VM/MMCL/PME/CB1/PIP/PR-009 | Technical Specification ref |  |
| SAP PR No: |  | Technical Specification Date |  |
| WBS: | VM-1017-C-PME-CB1-PIP | WBS Budget total | USD 9,285,392.31 |
|  |  | WBS Budget balance | USD 7,769,233.41 |
|  |  | Value of current NFA | USD 1,570,250.00 |
|  |  | Estimate value for balance WBS | USD 6,198,983.41 |

- DESCRIPTION OF THE PACKAGE:

The scope this note covers the Supply of Parts and Components for enabling Modifications of Existing Slurry Pumps for Line 1 & Line 2 as per the table below.

| TAG NO./S | DESCRIPTION | QTY | MODIFICATION |
| --- | --- | --- | --- |
| 2120-SP-107, 108, 207 | Rougher Concentrate to VM Hydrocyclone Feed Pump Box | 3 | Upgradation: Wet End Assembly component, Fixed Speed V-Belt Drive Assembly |
| 2120-SP-109, 110, 209, 210 | Ball mill Hydrocyclone O'flow to Rougher Feed | 4 | Upgradation: Bare Shaft Pump Assembly, In-line Common Base, Gearbox with A/O cooler, HS & LS Couplings & Coupling Guard. |
| 2120-SP-103, 104, 203, 204 | Ball mill discharges to AG mill discharge pump box | 4 | Upgradation: Wet End Assembly, Drive Guard & Side-by-side base, Slide rails for side-by-side motor mount, Fixed-speed V-Belt Drive Assembly & Motor (250HP) |
| 2120-SP-105, 106 | Vertimill cyclone overflow to finisher feed | 2 | Upgradation: Drive Guard & Side-by-side base, Slide rails for side-by-side motor mount & Fixed-speed V-Belt Drive Assembly |
| 2120-SP-205, 206 | Vertimill cyclone overflow to finisher feed | 2 | Upgradation: Drive Guard & Side-by-side base, Slide rails for side-by-side motor mount & Fixed-speed V-Belt Drive Assembly |
| 2120-SP-111, 112, 211, 212 | Tailing hydro separator underflow pumps | 4 | Upgradation: Fixed-speed V-Belt Drive Assembly |
| 2120-SP-113, 114, 213, 214 | Finisher concentrate pumps | 4 | Upgradation: Wet End Assembly, Fixed-speed V-Belt Drive Assembly & Motor (100HP) |
| 2120-SP-001, 002, 003, 004 | Concentrate thickener underflow pumps | 4 | Upgradation: Fixed-speed V-Belt Drive Assembly. |
| 2180-SP-001, 002, 003, 004 | Tailing thickener underflow pumps | 4 | Replacement: Bare-shaft Pump Assembly, Drive Guard & Side-by-side base, Slide rails for side-by-side motor mount & Fixed-speed V-Belt Drive Assembly |

Background

The Pellet Plant under implementation has a rated capacity of 7.0 MTPA and a design capacity of 7.5 MTPA to produce 100% DR-grade pellets. The Concentrator, however, is designed for a production capacity of 6.3 MTPA of DR-grade concentrate, with a mill feed rated capacity of 844 TPH and an overall recovery of approximately 30.8%. To maximise utilisation of the Pellet Plant capacity, there is a need to evaluate options for increasing the capacity of the Concentrator.

For the existing concentrator capacity of 6.3 MTPA, the grinding capacity of 20.4 MTPA requires a Run-of-Mine (ROM) feed of approximately 21.1 MTPA, considering dry cobber rejects. As per the Mine Plan, the ROM quantity can reach up to 24 MTPA. Accordingly, the gap of approximately 2.9 MTPA between the available ROM and the current requirement can be utilised to produce additional concentrate, subject to the addition of grinding capacity.

Further, based on test work carried out by Metso and Dr. Biswal in India, it was observed that overall yield can be improved by feeding a finer particle size to the Rougher Magnetic Separators. The optimal feed size was identified as approximately 175 microns, compared to the original design size of 600 microns. The test results also indicated a potential increase in overall weight recovery from 29–29.3% to 30.4–30.9%, from ROM to concentrate after flotation.

Based on these findings, a 6.3 MTPA Gap Analysis Study was carried out, which indicated that the addition of extra grinding capacity could enhance the concentrator capacity to 7.3 MTPA, while maintaining the mining capacity at up to 24 MTPA.

Action Taken

Considering the above, it was decided to implement the Verti Mill Project, comprising three Verti Mills of 4,500 HP each, along with associated equipment such as hydro cyclones, pumps, and auxiliaries, to cater to secondary grinding from 175 microns to 45 microns as part of the enhanced concentrator capacity of 7.3 MTPA. This enhancement necessitated a review of the existing slurry pumps.

Accordingly, a technical enquiry was issued for the modification of the existing slurry pumps supplied by FLSmidth, based on the mass and water balance duly vetted by the MMCPL team. The vendor has identified the required modifications to meet the revised operating conditions, and the recommended changes along with the updated operating parameters have been provided.

It may be noted that during initial commissioning and until the respective Verti Mills are installed, the plant shall be operated at a turned-down capacity. However, the modifications identified are required to be implemented to cater to both operating scenarios, namely 7.3 MTPA operation as well as turned-down capacity operation.

Requirement per 7.3 MTPA Flow Sheet

| S NO | PUMP NO. | NO OF PUMPS | ORIGINAL | NEW/REVISED |
| --- | --- | --- | --- | --- |
| 1 | 2120-SP-107,108,207 | 3 | Rougher Concentrate to Hydrocyclone Feed Pump Box | Rougher Concentrate to VM Hydrocyclone Feed Pump Box |
| 2 | 2120-SP-109,110,209,210 | 4 | ball mill cyclone feed pump box to ball mill cyclone | Ball mill Hydrocyclone Overflow to Rougher Feed |
| 3 | 2120-SP-103,104,203,204 | 4 | Ball mill discharge to primary screen | Ball mill discharge to AG mill discharge pump box |
| 4 | 2120-SP-105,106 - Line 1 | 2 | Concentrate hydro separator to finisher feed | Verti mill cyclone overflow to finisher feed |
| 5 | 2120-SP-205,206 Line 2 | 2 | Concentrate hydro separator to finisher feed | Verti mill cyclone overflow to finisher feed |
| 6 | 2120-SP-111,112,211,212 | 4 | Tailing hydro separator underflow pumps | Tailing hydro separator underflow pumps |
| 7 | 2180-SP-001,002, 003,004 | 4 | Tailing thickener underflow pumps | Tailing thickener underflow pumps |
| 9 | 2120-SP-113,114,213,214 | 4 | Finisher concentrate to fine screen | Finisher concentrate to concord cell |
| 10 | 2120-SP-001,002,003,004 | 4 | Concentrate thickener underflow pumps | Concentrate thickener underflow pumps |

Revised Duty Conditions as per 7.3 MTPA Mass & Water Balance

| Sr# | Pump No. | Dis dia (mm) |  | Flow (m3/h) |  | Discharge Head (MCL) |  | Motor (HP) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Existing | Revised | Existing | Revised | Existing | Revised | Existing | Revised |
| 1 | 2120-SP-107,108,207 | 300 | 300 | 1382 | 764 | 10 | 8 | 125 | 44 |
| 2 | 2120-SP-109,110,209,210 | 350 | 550 | 2130 | 4040 | 50 | 31 | 900 | 685 |
| 3 | 2120-SP-103,104,203,204 | 250 | 450 | 1120 | 2375 | 53 | 10 | 600 | 185 |
| 4 | 2120-SP-105,106 - Line 1 | 350 | 350 | 1603 | 1988 | 35 | 42 | 400 | 486 |
| 5 | 2120-SP-205,206 Line 2 | 350 | 350 | 1603 | 1988 | 35 | 38 | 400 | 430 |
| 6 | 2120-SP-111,112,211,212 | 250 | 250 | 725 | 830 | 45 | 39 | 300 | 220 |
| 7 | 2180-SP-001,002 (Common for three lines) | 300 | 300 | 964 | 1238 | 27 | 42 | 200 | 313 |
| 8 | 2180-SP-003,004 | 300 | 300 | 964 | 1238 | 18 | 32 | 125 | 233 |
| 9 | 2120-SP-113,114,213,214 (Common for three lines) | 250 | 300 | 845 | 850 | 34 | 16 | 250 | 84 |
| 10 | 2120-SP-001,002,003,004 | 200 | 200 | 192 | 221 | 37 | 29 | 150 | 72 |

BID EVALUATION

| 1 | M/s FLSmidth |
| --- | --- |

The technical parameters were provided to M/s FLS, based on which M/s FLS has identified the modifications required in the existing pumps to achieve the new feed requirements.

As this is modification work on existing pumps for line 1 and line 1, offers were sought only from original equipment manufacturer, FLS.

Key Features and recommendations from M/s FLSmidth for modifications to the existing pumps to meet the new duty requirements

| ITEM | EXISTING | MODIFICATION |
| --- | --- | --- |
| 2120-SP-107, 108, 207 | millMAX 16x14-39 MMC W/F, SxS, V-belt | Vendor has recommend converting to a millMAX 12x10-30 using the existing power frame and motor by swapping the wet-end parts and changing the belt-drive and sheave on the existing pump assembly to suit the new duty conditions. |
| 2120-SP-109, 110, 209, 210 | millMAX 14x12-36 MMD W/F, In-Line w/Gear Box | The existing pump cannot meet the new process requirements. The Vendor has recommended a millMAX 24x20-54, 5 vanes with MME power frame for improved efficiency and reliable operation. Concrete work may be needed for installation. The existing motor can be retained, minimizing additional cost. |
| 2120-SP-103, 104, 203, 204 | millMAX 12x10-30 MMD W/F, In-Line w/Gear Box | The existing pump cannot meet the new process requirements. The Vendor has recommended a millMAX 20x18-46 with Vbelt drive (SxS) due to the process change. The pump is currently equipped with a gearbox for high power, but the slurry power calculated is now lower, eliminating the need for the gearbox. Instead, a belt-drive arrangement with a 250 HP, 12-pole motor is suitable for the new duty conditions. |
| 2120-SP-105, 106 - Line 1 | millMAX 14x12-36 MMD W/F, SxS, V-BELT | The existing 14x12-36 pump with MMD frame can be retained for this duty; however, due to the increased slurry power requirement, the vendor recommended upgrading to a 600 HP, 6P motor. Alternatively, as suggested by the client, the available 600 HP, 4P motor from the ball mill discharge pumps may be reused which resulting in a larger sheave on the pump side. Accordingly, modification of the motor mounting arrangement, new belt drive selection (sheaves and belts), and belt guard modification will be included in our scope, with final drive details to be confirmed during the detailed engineering stage. The existing 400 HP motor is not suitable for the revised duty conditions. |
| 2120-SP-205, 206 Line 2 | millMAX 14x12-36 MMD W/F, SxS, V-BELT | The existing 14x12-36 pump with MMD frame can be retained for this duty; however, due to the increased slurry power requirement, the vendor hass recommend upgrading to a 600 HP, 6P motor. Alternatively, as suggested by the client, the available 600 HP, 4P motor from the ball mill discharge pumps may be reused which resulting in a larger sheave on the pump side. Accordingly, modification of the motor mounting arrangement, new belt drive selection (sheaves and belts), and belt guard modification will be included in our scope, with final drive details to be confirmed during the detailed engineering stage. The existing 400 HP motor is not suitable for the revised duty conditions. |
| 2120-SP-111, 112, 211, 212 | millMAX 10x8-24 MMC W/F, SxS, V-BELT | The existing millMAX 10x8-24 with MMC frame pump can be used. However, the belt drive will require a change to suit the new duty condition. |
| 2180-SP-001, 002, 003, 004 | millMAX 12x10-16 MMC W/F, SxS, V-BELT | Thickener Underflow pumps (2180-SP-001, 002, 003, 004) were confirmed completely submerged and therefore require full replacement. Accordingly, the vendor has included complete replacement pumps in our scope. The existing site motor, currently installed on the Vertimill Cyclone OF duty, will be retained and reused for these pumps. |
| 2120-SP-113, 114, 213, 214 | millMAX 10x8-24 MMB W/F, SxS, V-BELT | The existing pump cannot meet the new process requirements. The vendor recommended upgrading to a millMAX 12x10-30. The wet-end parts can be swapped onto the existing pump, and the belt drive will require a sheave change. To maintain a belt ratio of less than 3:1, a new 8- pole, 100 HP motor has been offered. |
| 2120-SP-001, 002, 003, 004 | millMAX 6x4-16 MMB W/F, SxS, V-BELT | The existing millMAX 6x4-16 with MMB frame pump can be used. However, the belt drive will require a change to suit the new duty conditions. |

Evaluation of Offers

- M/s FLS has submitted the offer for the modification required in the pumps along with the Technical data sheet and the curves for the line #1 & 2 slurry pumps.

- M/s FLS Confirmed meeting the updated duty conditions for 7.3 MTPA upgradation.

- Also, the Detailed List of Modification required is provided by M/s FLS.

Delivery Schedule

- Approval drawings: to begin in 3 - 4 weeks on a rolling basis after receipt of Purchase Order or supplied certified motor prints.

- Signed Approval: 1 - 2 weeks after the date of drawing submittal.

- Release for fabrication will begin once all changes have been approved by both.

- Shipment of equipment: 14 - 18 weeks after the date of release for fabrication.

Technical Recommendation

The Technical and Engineering team has evaluated the offer received from M/s FLSmidth. Based on detailed analysis the vendor is technically acceptable for ordering components and equipments for Modification of Existing Slurry Pumps for Line 1 & Line 2.

COMMERCIAL COMPARISON

| Vendor | M/s FLSmidth |
| --- | --- |
| Quotation | MIN-2511-206403, Rev 4 |
| Date | 25-Feb-2026 |
| Quoted Price (USD) | 2,781,690.00 |
| Negotiated Price (USD) | 1,570,250.00 |
| Import duties & Tariff ($)** (India – 50%) | 385,165.00 |
| Estimated Logistic Cost (USD) | 60,000.00 |
| Landed Cost (USD) | 2,015,415.00 |
| Delivery timeline | 18-24 weeks (Ex works, Arakkonam & Ex-Works Tucson) from the date of PO |

Note:

**Supply against Tags 2120-SP-109, 2120-SP-110, 2120-SP-209, and 2120-SP-210 shall be on an Ex Works-Tucson, USA basis. Accordingly, no import duties or tariffs are applicable for these items. Import duties and tariffs shall be applicable only for materials supplied on an Ex Works-Arakkonam, India basis.

B. RECOMMENDATION:

It is recommended to place purchase order on M/s FLSmidth, USA, with brief terms & conditions negotiated are as listed below:

| Final Value | USD 1,570,250.00 (Ex works Arakkonam, India & Ex-Works Tucson, USA) as per final technical scope agreed during technical evaluation. Freight & Insurance cost to the account of MMCL. |
| --- | --- |
| Payment Terms | Payment shall be as per below: o 10% advance shall be paid against submission of unconditional & irrevocable SBLC of equivalent amount. o 5% shall be released against the approval of GA Drawings o 35% shall be released against manufacturing clearance. o Balance 50% shall be released against material readiness prior to dispatch with the submission of 10% PBG valid till warranty period. |
| Delivery Schedule | The delivery shall be 18-24 weeks after the date of Purchase Order. |
| Warranty Period | The Warranty Period of the GOODS supplied will be 18 months from the date of installation or 24 months from the date of supply whichever is earlier. |
| Other Terms & Conditions | As per STC & GTC. |
| SBLC & PBG | SBLC of 10% for advance payment & PBG of 10 % for performance |

C. REASONS FOR RECOMMENDATION:

- M/s FLSmidth is technically acceptable.

- M/s FLSmidth has successfully executed previous orders and has met MMCL timeline.

- M/s FLS Confirmed meeting the updated duty conditions for 7.3 MTPA upgradation.

In view of above, it is recommended to place order for the Modification of Slurry Pumps for Capacity Enhancement of Line 1 & 2 with M/s FLSmidth for Value USD 1,570,250.00 (Ex works Arakkonam, India & Ex-Works Tucson, USA).

| Prepared & Initiated By | BHAWESH JHA / KUMAR PIYUSH AMAN / SATYEN SINHA |  |
| --- | --- | --- |
| Cost Control / Planning | MANINDRA AGRAWAL / MAHESH KOMMURU |  |
| Finance & Account | SUNIL AGRAWAL / LALIT RUSTAGI |  |
| Recommendation & Approval Committee | SUBBARAO NAMALA |  |
|  | MOHAMMAD RIZWAN |  |
| Approved by | RAKESH KANKANALA |  |
|  | AMIT SWARNKAR |  |

Enclosure –

1.	Final No Regret offer from M/s FLSmidth

2.	Technical Recommendation & Email Confirmation

3.    PR Copy